## Test Scenarios
Phase scenario suite — manual comparison checklist
Generated by tools/test-mcp/generate_test_scenarios_xlsx.py. Each scenario lists its canonical flow steps and the latest run status. Use the rightmost column for ad-hoc manual notes (false-greens, skipped steps, environment quirks). Status colours: green=ok, amber=deferred, orange=deferred-manual, red=flaky/failing.
Phase A.1 — Inbox Triage
2 use_cases both event-triggered on `gmail.message.received` (parallel, not chained). · Introduced in C6 (2026-04-27) · Driver: `tools/test-mcp/e2e_phase_a.py --scenario inbox`
Intent (prompt used): Watch my Gmail inbox. On every new message, classify it as urgent / followup / fyi. When the classification is 'urgent', also draft a short reply for me to review before sending. Both capabilities trigger directly on a new Gmail message arriving — the draft capability does NOT chain off the classifier; it runs in parallel and only emits its draft when its own classifier-style check judges the message urgent.
Flow step | Status | Notes
Preflight — /health probe returns ok | ok
startBuildFromIntent → session created, persona row enabled=false | ok
LLM emits clarifying questions, driver answers via cellKey-keyed batch | ok
All gates open, LLM emits agent_ir → phase: draft_ready | ok
wait_for_agent_ir defensive poll succeeds | ok
triggerBuildTest → tool tests run, phase: test_complete | ok
promoteBuildDraft → single-tx commit; persona enabled=true | ok
Acceptance: 2 use_cases produced | ok
Acceptance: 2 event_listener triggers on `gmail.message.received` | ok
Acceptance: 1 assertion / 3 subs / 3 tools / 2 triggers landed | ok
Cleanup: deleteAgent succeeds | ok
Phase A.2 — Project Coordinator
4 use_cases — 3 collectors (Linear/GitHub/Calendar) + 1 digest assembler chained on `*.brief.ready` events. Validates rule D (producer/publisher chain split). · Introduced in C6 (2026-04-27) · Driver: `tools/test-mcp/e2e_phase_a.py --scenario coordinator`
Intent (prompt used): Every Monday at 8am local time, build a single weekly digest covering three sources: my Linear assigned issues, my GitHub pull requests awaiting review, and today's Google Calendar events. Each source is its own capability so I can turn off any one independently. Save the digest as a single markdown file in my local drive — never email or message.
Flow step | Status | Notes
Preflight — /health probe returns ok | ok
startBuildFromIntent → session created, persona row enabled=false | ok
LLM emits clarifying questions, driver answers via cellKey-keyed batch | ok
All gates open, LLM emits agent_ir → phase: draft_ready | ok
wait_for_agent_ir defensive poll succeeds | ok
triggerBuildTest → tool tests run, phase: test_complete | ok
promoteBuildDraft → single-tx commit; persona enabled=true | ok
Acceptance: 4 use_cases produced (rule D fired — collectors split + assembler) | ok
Acceptance: 4 triggers landed | ok
Acceptance: brief.ready event chain wired between collectors and assembler | ok
Cleanup: deleteAgent succeeds | ok
Phase B — Chained personas X→Y→Z
3 personas: HN scraper → Summarizer → Archivist. Validates cross-persona event chain (auto-`source_filter='*'` for inbound listens). · Introduced in C6 (2026-04-27) · Driver: `tools/test-mcp/e2e_phase_b.py`
Intent (prompt used): [Persona X — head] Be a Hacker News digest scraper. Once an hour, fetch the top 3 stories from the Hacker News RSS feed (https://news.ycombinator.com/rss) and emit each as a draft news item for downstream personas to summarize. Single capability, schedule-triggered. (+event-name discipline lock for `news.draft.captured`.) [Persona Y — middle] Listen for `news.draft.captured` events. For each draft, write a 2-sentence summary and emit it for the notes poster persona to archive. Emit `news.summary.ready` when the summary is ready. (+event-name discipline lock for both names.) [Persona Z — tail] Listen for `news.summary.ready` events. For each summary, append a markdown line to my local drive notes file at `news/digest.md`. (+event-name discipline lock for `news.summary.ready`.)
Flow step | Status | Notes
Preflight — /health probe returns ok | ok
Build persona X (scraper) — schedule trigger, emits `news.draft.captured` | ok
Build persona Y (summarizer) — listens `news.draft.captured`, emits `news.summary.ready` | ok
Build persona Z (archivist) — listens `news.summary.ready`, writes to local-drive | ok
Promote each — auto-`source_filter='*'` defaulted for cross-persona listens | ok
Fire X manually → X executes | ok
Y picks up automatically (cross-persona event delivered) | ok
Z picks up automatically | ok
Acceptance: cascade.full_chain reports ok | ok
Cleanup: deleteAgent for X, Y, Z | ok
Phase C — Output diversity (vector_db scenario)
Persona writes facts to `personas_vector_db` connector via `vector_db_insert` tool. · Introduced in C6 (2026-04-27) · Driver: `tools/test-mcp/e2e_phase_c.py --scenario vector_db`
Intent (prompt used): Once a day at 8am, write a one-paragraph summary of yesterday's activity into my built-in vector knowledge base so I can search across past days later. Single capability, schedule-triggered. Output target: `personas_vector_db` connector — index the summary as a single document with date as the title.
Flow step | Status | Notes
Preflight — /health probe returns ok | ok
startBuildFromIntent → session created, persona row enabled=false | ok
LLM emits clarifying questions, driver answers via cellKey-keyed batch | ok
All gates open, LLM emits agent_ir → phase: draft_ready | ok
wait_for_agent_ir defensive poll succeeds | ok
triggerBuildTest → tool tests run, phase: test_complete | ok
promoteBuildDraft → single-tx commit; persona enabled=true | ok
Acceptance: persona uses `personas_vector_db` connector | ok
Acceptance: tool list includes `vector_db_insert` + `date_utilities` | ok
Cleanup: deleteAgent succeeds | ok
Phase C — Output diversity (notion scenario)
Persona logs daily status to Notion page; uses `notion` + `gmail` connectors. · Introduced in C6 (2026-04-27) · Driver: `tools/test-mcp/e2e_phase_c.py --scenario notion`
Intent (prompt used): Every morning at 9am, append a status page to my Notion workspace summarising overnight activity. Single capability, schedule-triggered. Output target: Notion — create one new page per run in a configured database.
Flow step | Status | Notes
Preflight — /health probe returns ok | ok
startBuildFromIntent → session created, persona row enabled=false | ok
LLM emits clarifying questions, driver answers via cellKey-keyed batch | ok
All gates open, LLM emits agent_ir → phase: draft_ready | ok
wait_for_agent_ir defensive poll succeeds | ok
triggerBuildTest → tool tests run, phase: test_complete | ok
promoteBuildDraft → single-tx commit; persona enabled=true | ok
Acceptance: persona uses `notion` + `gmail` connectors | ok
Acceptance: `notion_create_page` tool listed (+ web/gmail search) | ok
Cleanup: deleteAgent succeeds | ok
Phase C — Output diversity (github scenario)
Weekly priority tracker creates GitHub issues; uses `github` + `personas_database`. · Introduced in C6 (2026-04-27) · Driver: `tools/test-mcp/e2e_phase_c.py --scenario github`
Intent (prompt used): Every Monday at 7am, file a single GitHub issue summarising weekly priorities into a configured repo. Single capability, schedule-triggered. Output target: GitHub — issue creation.
Flow step | Status | Notes
Preflight — /health probe returns ok | ok
startBuildFromIntent → session created, persona row enabled=false | ok
LLM emits clarifying questions, driver answers via cellKey-keyed batch | ok
All gates open, LLM emits agent_ir → phase: draft_ready | ok
wait_for_agent_ir defensive poll succeeds | ok
triggerBuildTest → tool tests run, phase: test_complete | ok
promoteBuildDraft → single-tx commit; persona enabled=true | ok
Acceptance: persona uses `github` + `personas_database` connectors | ok
Acceptance: `github_create_issue` tool listed (+ list/search/sql) | ok
Cleanup: deleteAgent succeeds | ok
Phase C — Output diversity (titlebar scenario)
Heartbeat monitor surfaces output to the desktop titlebar; no external connectors. Validates fix H (`notification_channel_array` v3.1 shape). · Introduced in C6 (2026-04-27) · Driver: `tools/test-mcp/e2e_phase_c.py --scenario titlebar`
Intent (prompt used): Every hour on the hour, surface a desktop / titlebar notification with a single-sentence status update — NO file writes, NO event emissions, NO external connector. Just a notification.
Flow step | Status | Notes
Preflight — /health probe returns ok | ok
startBuildFromIntent → session created, persona row enabled=false | ok
LLM emits clarifying questions, driver answers via cellKey-keyed batch | ok
All gates open, LLM emits agent_ir → phase: draft_ready | ok
wait_for_agent_ir defensive poll succeeds | ok
triggerBuildTest → tool tests run, phase: test_complete | ok
promoteBuildDraft → single-tx commit; persona enabled=true | ok
Acceptance: no external connectors | ok
Acceptance: notification channel `built-in/titlebar` lands on persona row | ok
Cleanup: deleteAgent succeeds | ok
Phase D — auto_triage build-shape
Verifies build prompt rule 21 fires `mode: "auto_triage"` and promote preserves it on `design_context.useCases[]`. Build-shape only — runtime verified by Phase D2. · Introduced in C7 (2026-04-28) · Driver: `tools/test-mcp/e2e_phase_d.py`
Intent (prompt used): Once a day at 9am, scan my local-drive 'inbox' folder for new support emails I dropped there overnight. For each email, decide if it deserves a reply this morning by checking it against three decision principles: (1) the sender is a paying customer, (2) the subject mentions a P1/P2 incident, (3) it cites a broken feature. AUTO-TRIAGE the verdict — surface compliant ones in a titlebar notification, silently archive the rest. Use review_policy.mode = 'auto_triage'. No human gate.
Flow step | Status | Notes
Preflight — /health probe returns ok | ok
startBuildFromIntent → session created, persona row enabled=false | ok
LLM emits clarifying questions, driver answers via cellKey-keyed batch | ok
All gates open, LLM emits agent_ir → phase: draft_ready | ok
wait_for_agent_ir defensive poll succeeds | ok
triggerBuildTest → tool tests run, phase: test_complete | ok
promoteBuildDraft → single-tx commit; persona enabled=true | ok
Acceptance: at least one UC has `review_policy.mode == "auto_triage"` | ok
Acceptance: `last_design_result.persona.decision_principles[]` non-empty (informational) | ok
Acceptance: 0 pending manual_reviews for the fresh persona (smoke check) | ok
Cleanup: deleteAgent succeeds | ok
Phase D2 — auto_triage runtime E2E
Promotes a Phase-D-shaped persona, calls `synthesizeManualReview` (test bridge), polls until evaluator finalises verdict, asserts `policy_events` carries the `review.auto_triage.{approved¦rejected¦fallback}` audit tag. · Introduced in C8 (2026-04-28) · Driver: `tools/test-mcp/e2e_phase_d2.py`
Intent (prompt used): Once a day at 9am, scan my local-drive 'inbox' folder for new support emails I dropped there overnight. For each email, decide if it deserves a reply this morning by checking it against three decision principles: (1) the sender is a paying customer, (2) the subject mentions a P1/P2 incident, (3) it cites a broken feature. AUTO-TRIAGE the verdict — surface compliant ones in a titlebar notification, silently archive the rest. Use review_policy.mode = 'auto_triage'. No human gate. [After promote, the driver synthesizes a `manual_review` row via the C8 `synthesize_manual_review` test bridge command — title "P1 incident — vault sync stuck for paying customer", description matching all three decision principles, severity "high".]
Flow step | Status | Notes
Preflight — /health probe returns ok | ok
startBuildFromIntent → session created, persona row enabled=false | ok
LLM emits clarifying questions, driver answers via cellKey-keyed batch | ok
All gates open, LLM emits agent_ir → phase: draft_ready | ok
wait_for_agent_ir defensive poll succeeds | ok
triggerBuildTest → tool tests run, phase: test_complete | ok
promoteBuildDraft → single-tx commit; persona enabled=true | ok
Find auto_triage UC on promoted persona's design_context | ok
synthesizeManualReview bridge call returns {reviewId, executionId} | ok
Poll listManualReviews until status leaves Pending (timeout 120s) | ok
Assert review row landed Approved / Rejected / Resolved | ok
getPolicyEventsForExecution returns at least one auto_triage audit row | ok
Latest run: verdict APPROVED in 8s, audit tag review.auto_triage.approved | ok
Cleanup: deleteAgent succeeds | ok
Phase E — Preload-error reload (deferred-manual)
WebView2 stale-chunk recovery — verifies `vite:preloadError` listener reloads cleanly after a tauri-cli rebuild. Listener has 6 unit tests; live verification is a manual checklist. · Introduced in C6 (2026-04-27) · Driver: `(manual — see C7-handoff-2026-04-28.md §Phase E)`
Intent (prompt used): (no build INTENT — Phase E is a manual checklist for the WebView2 stale-chunk reload path. Repro: launch dev with test-automation, navigate to a non-default route to force a lazy chunk load, touch any Rust source file to trigger a tauri-cli rebuild + restart, click around in the WebView once the backend is back up. Watch for `vite:preloadError — reloading to pick up fresh chunks` console log + clean reload. Verify 30s throttle by deleting a chunk file mid-flight — the second preloadError within 30s should log the throttle suppression instead of reloading.)
Flow step | Status | Notes
Launch dev with test-automation; navigate to a non-default route (lazy chunk) | deferred-manual
Touch any Rust source file to force tauri-cli rebuild + restart | deferred-manual
After backend returns, click around in the WebView | deferred-manual
Watch for `vite:preloadError — reloading to pick up fresh chunks` log + clean reload | deferred-manual
Verify 30s throttle by deleting a chunk file mid-flight | deferred-manual
Listener unit tests (preloadErrorRecovery.test.ts, 6 cases) | ok
Phase F — Multi-language build (Czech preset)
Verifies localised fields (mission/principles/decision_principles/operating_instructions) come back in target language while UC ids and trigger_type strings stay English. · Introduced in C7 (2026-04-28) · Driver: `tools/test-mcp/e2e_phase_f.py --language cs`
Intent (prompt used): Vytvoř pro mě denního asistenta, který každé ráno v 8:00 shrne mé poznámky z předchozího dne uložené ve složce na mém disku. Žádné ruční schvalování — výstup zobraz v lište stavu. Bez paměti mezi dny.
Flow step | Status | Notes
Preflight — /health probe returns ok | ok
startBuildFromIntent → session created, persona row enabled=false | ok
LLM emits clarifying questions, driver answers via cellKey-keyed batch | ok
All gates open, LLM emits agent_ir → phase: draft_ready | ok
wait_for_agent_ir defensive poll succeeds | ok
triggerBuildTest → tool tests run, phase: test_complete | ok
promoteBuildDraft → single-tx commit; persona enabled=true | ok
Acceptance: localised field contains target-language diacritics (cz: čřšž etc.) | ok
Acceptance: UC ids contain NO target-language diacritics (English-stable) | ok
Acceptance: trigger_type strings contain NO target-language diacritics | ok
Cleanup: deleteAgent succeeds | ok
Phase F — Multi-language build (es / de / fr presets)
Same gates as the Czech preset, target language varies. `--strict-language-percentage 0.5` raises the diacritic-density bar. · Introduced in C7 (2026-04-28) · Driver: `tools/test-mcp/e2e_phase_f.py --language {es¦de¦fr}`
Intent (prompt used): [es] Crea un asistente matutino que cada mañana a las 8:00 me resuma las notas que añadí ayer en una carpeta de mi disco. Sin revisión humana — muestra el resultado en la barra de estado. Sin memoria entre días. [de] Erstelle mir einen morgendlichen Assistenten, der jeden Morgen um 8 Uhr meine Notizen vom Vortag aus einem Ordner auf meinem Laufwerk zusammenfasst. Keine manuelle Prüfung — zeige das Ergebnis in der Statusleiste. Kein Gedächtnis zwischen den Tagen. [fr] Crée-moi un assistant matinal qui chaque matin à 8h résume mes notes de la veille stockées dans un dossier de mon disque. Aucune revue manuelle — affiche le résultat dans la barre de statut. Sans mémoire entre les jours.
Flow step | Status | Notes
Run preset for `es` (Spanish) | ok
Run preset for `de` (German) | ok
Run preset for `fr` (French) | ok
All three localised in target language; identifiers stay English | ok
Phase G — Dry-run preview
Tiny single-capability persona; calls `simulateBuildDraft` + `getSimulationArtefacts` WITHOUT promoting. Verifies wiring correctness. · Introduced in C7 (2026-04-28) · Driver: `tools/test-mcp/e2e_phase_g.py`
Intent (prompt used): A simple notes summarizer. One capability: every morning at 8am local time, take any notes I added to a local-drive folder yesterday and produce a one-paragraph digest. Auto-publish (no review). Stateless.
Flow step | Status | Notes
Preflight — /health probe returns ok | ok
startBuildFromIntent → session created, persona row enabled=false | ok
LLM emits clarifying questions, driver answers via cellKey-keyed batch | ok
All gates open, LLM emits agent_ir → phase: draft_ready | ok
wait_for_agent_ir defensive poll succeeds | ok
triggerBuildTest → tool tests run, phase: test_complete | ok
Resolve first capability id via getPersonaDetail | ok
simulateBuildDraft({useCaseId}) — backend snapshots design_context, dispatches simulate | ok
getSimulationArtefacts({executionId}) returns {executionId, reviews[], memories[]} | ok
Acceptance: response shape (executionId round-trips, both arrays are arrays) | ok
Cleanup: deleteAgent succeeds | ok
Phase H — Webhook trigger + smee auto-bind
GitHub push → Slack relay scenario. Watches for `acceptsWebhookSource: true` clarifying-question, attaches per-run unique smee URL via typed-payload bridge call. · Introduced in C7 (2026-04-28) · Driver: `tools/test-mcp/e2e_phase_h.py`
Intent (prompt used): React in real time when GitHub fires a `push` webhook on my main repo. Forward the payload to a Slack channel as a brief one-line summary so the team sees the commit immediately. No batching, no schedule — webhook trigger only.
Flow step | Status | Notes
Preflight — /health probe returns ok | ok
startBuildFromIntent → session created, persona row enabled=false | ok
LLM emits clarifying questions, driver answers via cellKey-keyed batch | ok
All gates open, LLM emits agent_ir → phase: draft_ready | ok
wait_for_agent_ir defensive poll succeeds | ok
triggerBuildTest → tool tests run, phase: test_complete | ok
promoteBuildDraft → single-tx commit; persona enabled=true | ok
During Q&A: detect `acceptsWebhookSource: true` question | ok
Submit smee URL via answerBuildQuestionWithWebhookSource (typed payload) | ok
Acceptance: IR has at least one webhook trigger | ok
Acceptance: webhook trigger config carries `smee_channel_url` matching submitted URL | ok
Acceptance: smee_relays row exists with target_persona_id == new persona, channel_url + event_filter match | ok
Cleanup: deleteAgent succeeds | ok
Phase I — Clockify monthly-invoice scenario
2-capability persona (Generate Invoice + Prepare Email Draft) sharing a monthly schedule trigger. UC1 review_policy=never, UC2=always. 7 acceptance gates. · Introduced in C7 (2026-04-28) · Driver: `tools/test-mcp/e2e_phase_i.py`
Intent (prompt used): Generate monthly invoices from my Clockify time entries. On the 1st of each month at 9am, read last month's billable entries from Clockify, compose an itemized invoice that matches my saved template (I'll attach a sample), then prepare a draft email to my accountant with the invoice attached. Two capabilities: (1) Generate Invoice — produces the invoice document from Clockify data; (2) Prepare Email Draft — composes the message body and attaches the invoice. I want to review the email draft before it leaves my account.
Flow step | Status | Notes
Preflight — /health probe returns ok | ok
startBuildFromIntent → session created, persona row enabled=false | ok
LLM emits clarifying questions, driver answers via cellKey-keyed batch | ok
All gates open, LLM emits agent_ir → phase: draft_ready | ok
wait_for_agent_ir defensive poll succeeds | ok
triggerBuildTest → tool tests run, phase: test_complete | ok
promoteBuildDraft → single-tx commit; persona enabled=true | ok
G2: 2 use_cases produced | ok
G3: schedule trigger present (cron `0 9 1 * *`) | ok
G4: clockify connector visible (persona-level OR per-UC tool_hints) | ok
G5: email connector visible (gmail / resend / sendgrid / etc.) | ok
G6: at least one UC has human review (always or on_low_confidence) | ok
G7: design_context.useCases[i].review_policy carried through promote | ok
G9: last_design_result.persona.decision_principles non-empty (C7 hoist fix) | ok
Cleanup: deleteAgent succeeds | ok
Phase J — Documentation archiver
2-UC scenario combining webhook+smee (Phase H plumbing) and reference attachment (Phase I plumbing, opportunistic). UC1 webhook-driven KB ingest, UC2 on-demand digest. · Introduced in C8 (2026-04-28) · Driver: `tools/test-mcp/e2e_phase_j.py`
Intent (prompt used): Documentation archiver. Two capabilities. UC1: when GitHub fires a `push` webhook (forwarded via https://smee.io/phase-j-<random-hex>, event_filter `github.push`), parse the changed markdown files and store each as a KB fact. UC2: on demand only, output a short digest of recent KB facts. Auto-publish both — no human review. [Note: the `<random-hex>` segment is regenerated per run via uuid.uuid4().hex[:12] so re-runs don't collide on the smee_relays channel_url UNIQUE constraint. Pasting the URL verbatim hits rule 24's SKIP path and bypasses the typed-payload question.]
Flow step | Status | Notes
Preflight — /health probe returns ok | ok
startBuildFromIntent → session created, persona row enabled=false | ok
LLM emits clarifying questions, driver answers via cellKey-keyed batch | ok
All gates open, LLM emits agent_ir → phase: draft_ready | ok
wait_for_agent_ir defensive poll succeeds | ok
triggerBuildTest → tool tests run, phase: test_complete | ok
promoteBuildDraft → single-tx commit; persona enabled=true | ok
During Q&A: typed-payload listener for acceptsWebhookSource (with smee URL pasted in INTENT, rule 24 SKIP path can fire instead) | ok
Acceptance: at least 2 use_cases | ok
Acceptance: webhook trigger present | ok
Acceptance: webhook trigger config carries smee_channel_url matching INTENT | ok
Acceptance: smee_relays row exists with target_persona_id matching | ok
Acceptance: digest UC has non-webhook trigger (manual / no row) | ok
Latest run: smee_relays_created=1, all 5 gates green | ok
Cleanup: deleteAgent succeeds | ok
Phase K — Video narration (build-shape only)
Verifies build pipeline composes a narrated-video persona enumerating google_gemini (vision) + elevenlabs (TTS). Runtime blocked on TTS impl + ffmpeg connector. · Introduced in C8 (2026-04-28) · Driver: `tools/test-mcp/e2e_phase_k.py`
Intent (prompt used): Make a narrated video on demand. I drop a folder of image frames into local-drive. For each frame, use Gemini Vision to write a one-sentence caption describing what's happening. Then use ElevenLabs to turn the captions into spoken audio. Final output: a video file with frames + spoken narration. Manual / on-demand trigger only — I'll invoke when frames are ready. Auto-publish, no human review.
Flow step | Status | Notes
Preflight — /health probe returns ok | ok
startBuildFromIntent → session created, persona row enabled=false | ok
LLM emits clarifying questions, driver answers via cellKey-keyed batch | ok
All gates open, LLM emits agent_ir → phase: draft_ready | ok
wait_for_agent_ir defensive poll succeeds | ok
triggerBuildTest → tool tests run, phase: test_complete | ok
promoteBuildDraft → single-tx commit; persona enabled=true | ok
Acceptance: at least one use_case | ok
Acceptance: design_context references google_gemini connector | ok
Acceptance: design_context references elevenlabs connector | ok
Acceptance: NO webhook trigger (scenario is on-demand) | ok
Latest run: 1 UC `Video Narrator`, manual trigger, both connectors landed | ok
Runtime execution (synthesise audio + compose video): not implementable today | deferred
Cleanup: deleteAgent succeeds | ok